## Exercise 5.1
Primary Structure Optioneering Matrix
| Project Scenario |  |  | Assessment Criteria
| Structural Options | MMC Category/Type |  | Design Integrity | Potential Flexibility | Carbon Reduction | Statutory Compliance | Suitability | Cost Certainty | Critical Path & Programme | Sequencing & Complexity | Supply Chain Capacity | Offsite Logistics | Nuisance Reduction | Site Operations & Logistics | Score | Impact
| Steel Frame Modules (HRS or LGS) | MMC 1 | 3D
| Engineered Timber Modules (LVL or CLT) | MMC 1 | 3D
| Milled Timber Modules | MMC 1 | 3D
| Pre-cast Concrete Modules | MMC 1 | 3D
| Structural Insulated Panels (SIPs) | MMC 2 | 2D
| Engineered Timber Panels (LVL or CLT) | MMC 2 | 2D
| Milled Timber Panels | MMC 2 | 2D
| Pre-cast Concrete Slab / Panel System | MMC 2 | 2D
| Light Steel Frame Insulated 2D Panels | MMC 2 | 2D
| Light Steel Frame Uninsulated 2D Panels | MMC 2 | 2D
| Light Steel Frame Kit (Pre-cut & Packaged) | MMC 2 | 2D
| Pre-cast Concrete Kit | MMC 3 | 2D
| Steel/Timber Hybrid construction | MMC 5 | 2D
| Concrete/LGS Hybrid construction | MMC 5 | 2D
| HRS/LGS Hybrid construction | MMC 5 | 2D
| Notes | [7 empty] | Definitions
1 | The purpose of the assessment is not to select one solution but to identify the best options to investigate in more detail. | [7 empty] | HRS - hot rolled steel
2 | Scoring principles as follows: | [7 empty] | LGS - Light gauge steel
| A definite Yes - Score as 1 (One) | [7 empty] | CLT - cross laminated timber
| A defininte No - Score as 0 (Zero) | [7 empty] | LVL - Laminated veneer lumber
| Not sure or maybe - Score as 0.5 (Point 5) | [7 empty] | SIPs - structural insulated panels
3 | Pre-cast Concrete Kit comprises beams, colunes, slabs and façade panels | [7 empty] | Hybrid - can be any combination of the above
4 | A score of 9 or more is high Impact; between 5 & 8 inclusive, medium impact and 4 or less is Low Impact
5 | High impact represents significant project benefit - allocate ownership for detailed consideration
6 | Medium impact elements will have limited project benefit - record for future reference subject to the outcome of the detailed consideration
7 | Low impact is little or no project benefit - record as not applicable